## Project Information and Screeni
Project Information
DPIA Reference No. | DPIA-2026-001
Project Name | HealthBridge CareConnect Platform
Project Description | Cloud-based digital healthcare platform providing patient registration, telemedicine, laboratory services, e-prescriptions, appointment scheduling, and payment processing.
Organisation | HealthBridge Digital Services Ltd
Department | Digital Health Services
Project Sponsor | Dr. Amina Yusuf
Project Manager | Ibrahim Musa
Data Protection Officer | Abdulmuizz Abdulrazaq
Information Security Lead | James Okafor
Legal Counsel | Fatima Bello
DPIA Start Date | 2026-08-01
Expected Go-Live Date | 2027-01-01
Version | 1
Assessment Status | In Progress
Processing Summary
Question | Answer
Purpose of Processing | Delivery of digital healthcare services.
Business Need | Improve access to healthcare through a secure online platform.
Categories of Data Subjects | Patients, Children, Doctors, Staff
Categories of Personal Data | Identity Data, Contact Data, Health Data, Financial Data
Sensitive Personal Data Processed? | Yes
Cross-Border Transfers? | Yes
Automated Processing? | Yes
Cloud Hosting? | Yes
DPIA Screening Quetionnaire
Does the project process personal data? | Yes
Does it process sensitive personal data? | Yes
Does it process children's data? | Yes
Is large-scale processing involved? | Yes
Is there systematic monitoring? | No
Are automated decisions made? | No
Does it involve new technologies? | Yes
Are international data transfers involved? | Yes
Are third-party processors involved? | Yes
Could the processing create high risks to individuals? | Yes
Screening Score
Response | Score
Yes | 1
No | 0
Result | 8
DPIA REQUIREMENT
DPIA Requirement | DPIA Required
Preliminary Risk Classification | Very High
DPO Recommendation | Proceed with Full DPIA
Muizz

## Processing Activities
Activity ID | Processing Activity | Purpose of Processing | Department | System/Application | Data Controller | Data Processor | Data Subjects | Personal Data | Special Personal Data | Lawful Basis | Recipients | International Transfer | Destination Country | Retention Period | Disposal Method | Existing Controls | Risk Level | DPIA Required | Remarks
PA001 | Patient Registration | Register new patients | Digital Health | CareConnect | HealthBridge | Cloud Provider | Patients, Parents/Guardians | Name, DOB, Address, Phone, Email, NIN | No | Consent | Customer Support | Yes | Netherlands | 7 Years | Secure Deletion | MFA, Encryption, RBAC | High | Yes
PA002 | Identity Verification | Verify patient identity | Operations | CareConnect | HealthBridge | Cloud Provider | Patients | NIN, Passport Photo | Yes | Legal Obligation | Verification Team | Yes | Netherlands | 7 Years | Secure Deletion | MFA, Encryption | Very High | Yes
PA003 | Appointment Booking | Schedule appointments | Medical Services | CareConnect | HealthBridge | Cloud Provider | Patients | Name, Contact Details | No | Contract | Doctors | Yes | Netherlands | 7 Years | Secure Deletion | MFA, RBAC | High | Yes
PA004 | Video Consultation | Deliver healthcare remotely | Medical Services | CareConnect | HealthBridge | Cloud Provider | Patients | Health Records, Consultation Notes | Yes | Vital Interest | Doctors | Yes | Netherlands | 10 Years | Secure Deletion | Encryption, Audit Logs | Very High | Yes
PA005 | Medical Records | Maintain patient records | Medical Services | EMR Module | HealthBridge | Cloud Provider | Patients | Medical History, Diagnosis | Yes | Vital Interest | Medical Staff | Yes | Netherlands | 10 Years | Secure Deletion | Encryption, RBAC | Very High | Yes
PA006 | Laboratory Results | Store laboratory reports | Laboratory | Laboratory Module | HealthBridge | Cloud Provider | Patients | Lab Results | Yes | Vital Interest | Laboratory Staff | Yes | Netherlands | 10 Years | Secure Deletion | Encryption | Very High | Yes
PA007 | Electronic Prescription | Generate prescriptions | Pharmacy | Prescription Module | HealthBridge | Cloud Provider | Patients | Prescription Data | Yes | Vital Interest | Pharmacy | Yes | Netherlands | 10 Years | Secure Deletion | Audit Logs | Very High | Yes
PA008 | Payment Processing | Process payments | Finance | Payment Gateway | HealthBridge | Payment Processor | Patients | Payment Information | No | Legitimate Interest | Payment Gateway | Yes | United States | 7 Years | Secure Deletion | Encryption | High | Yes
PA009 | SMS Notifications | Send reminders | Customer Care | SMS Gateway | HealthBridge | SMS Provider | Patients | Phone Number | No | Consent | SMS Provider | Yes | United States | 2 Years | Secure Deletion | DPA | High | Yes
PA010 | Email Notifications | Send updates | Customer Care | Email Service | HealthBridge | Email Provider | Patients | Email Address | No | Consent | Email Provider | Yes | Ireland | 2 Years | Secure Deletion | DPA | High | Yes

## Necessity and Proportionality
Assessment ID | Activity ID | Processing Activity | Purpose Clearly Defined? | Processing Necessary? | Processing Proportionate? | Lawful Basis Appropriate? | Data Minimisation Applied? | Accuracy Measures in Place? | Retention Appropriate? | Security Measures Adequate? | Transparency Provided? | Data Subject Rights Supported? | Compliance Score | Overall Compliance | Recommendation
NA001 | PA 001 | Patient Registration | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | 18 | Compliant | Proceed
NA002 | PA 002 | Identity Verification | Partially | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 19 | Compliant | Proceed
NA003 | PA 003 | Appointment Booking | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 18 | Compliant | Proceed
NA004 | PA 004 | Video Consultation | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | 18 | Compliant | Proceed
NA005 | PA 005 | Medical Records | No | Yes | Yes | Partially | Partially | Yes | Yes | Partially | Yes | Yes | 15 | Mostly Compliant | Proceed with Minor Improvements
NA006 | PA 006 | Laboratory Results | Partially | Yes | Partially | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 18 | Compliant | Proceed
NA007 | PA 007 | Electronic Prescription | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Yes | 18 | Compliant | Proceed
NA008 | PA 008 | Payment Processing | Yes | Yes | No | No | Yes | Yes | Yes | Yes | Yes | Yes | 16 | Mostly Compliant | Proceed with Minor Improvements
NA009 | PA 009 | SMS Notifications | Partially | Yes | Yes | Yes | Partially | Yes | Yes | No | Yes | Yes | 16 | Mostly Compliant | Proceed with Minor Improvements
NA010 | PA 010 | Email Notifications | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 20 | Compliant | Proceed

## Privacy Risk Assessment
Risk ID | Activity ID | Processing Activity | Privacy Risk | Data Protection Principle Affected | Likelihood | Impact | Inherent Risk Score | Inherent Risk Rating | Existing Control | Control Effectiveness | Residual Risk Score | Residual Risk Rating | Risk Treatment | Risk Owner | Target Date | Status | Remark
PR001 | PA 001 | Patient Registration | Unauthorized access to patient records | Integrity & Confidentiality | Possible | Severe | 15 | High | Encryption and Standard Contractual Clauses | Very Effective | 6 | Medium | Monitor | Information Security Manager | 2026-08-20 | Accepted
PR002 | PA 002 | Identity Verification | Identity theft | Integrity & Confidentiality | Rare | Severe | 5 | Medium | MFA and Standard Contractual Clauses | Effective | 3 | Low | Accept | Information Security Manager | 2026-08-21 | Accepted
PR003 | PA 003 | Appointment Booking | Unauthorized disclosure of appointments | Integrity & Confidentiality | Possible | Moderate | 9 | Medium | Audit Logs and Standard Contractual Clauses | Effective | 5 | Medium | Monitor | Information Security Manager | 2026-08-22 | Accepted
PR004 | PA 004 | Video Consultation | Interception of video sessions | Integrity & Confidentiality | Rare | Severe | 5 | Medium | Encryption and Standard Contractual Clauses | Very Effective | 2 | Low | Accept | Information Security Manager | 2026-08-23 | Accepted
PR005 | PA 005 | Medical Records | Data breach exposing health records | Integrity & Confidentiality | Possible | Major | 12 | High | Encryption and Standard Contractual Clauses | Very Effective | 5 | Medium | Monitor | IT Manager | 2026-08-24 | Accepted
PR006 | PA 006 | Laboratory Results | Unauthorized disclosure of laboratory reports | Integrity & Confidentiality | Possible | Major | 12 | High | MFA and Standard Contractual Clauses | Very Effective | 5 | Medium | Monitor | Information Security Manager | 2026-08-25 | Accepted
PR007 | PA 007 | Electronic Prescription | Prescription manipulation | Integrity & Confidentiality | Rare | Severe | 5 | Medium | MFA and Standard Contractual Clauses | Effective | 3 | Low | Accept | IT Manager | 2026-08-26 | Accepted
PR008 | PA 008 | Payment Processing | Financial information compromise | Accountability | Likely | Severe | 20 | Very High | Standard Contractual Clauses | Partially Effective | 16 | High | Escalate to NDPC | IT Manager | 2026-08-27 | Open
PR009 | PA 009 | SMS Notifications | Disclosure through incorrect recipient | Accountability | Rare | Moderate | 3 | Low | Incident Response Plan and Standard Contractual Clauses | Partially Effective | 2 | Low | Accept | IT Manager | 2026-08-28 | Accepted
PR010 | PA 010 | Email Notifications | Phishing or email compromise | Integrity & Confidentiality | Possible | Moderate | 9 | Medium | Security Awareness and Standard Contractual Clauses | Effective | 5 | Medium | Monitor | IT Manager | 2026-08-29 | Accepted

## Summary, Approval and Signoff
DPIA SUMMARY
DPIA Reference
Project Name
Organisation
Assessment Date | 2026-07-31
Current Version | 1
Assessment Status | In Review
RISK ASSESSMENT SUMMARY
Total Processing Activities | 10
Total Privacy Risks | 10
Very High Risks | 0
High Risks | 1
Medium Risks | 5
Low Risks | 4
APPROVAL MATRIX
Reviewer Role | Reviewer Name | Review Date | Decision | Comments | Signature
Project Sponsor | Dr. Amina Yusuf | 2026-09-01 | Approved |  | "Digitally Approved"
Project Manager | Ibrahim Musa | 2026-09-02 | Approved |  | "Digitally Approved"
Data Protection Officer | Abdulmuizz Abdulrazaq | 2026-09-03 | Approved |  | "Digitally Approved"
Information Security Manager | James Okafor | 2026-09-04 | Approved |  | "Digitally Approved"
Legal Counsel | Fatima Bello | 2026-09-05 | Approved |  | "Digitally Approved"
Compliance Officer | Mary Johnson | 2026-09-06 | Approved |  | "Digitally Approved"
Executive Management | CEO | 2026-09-07 | Approved |  | "Digitally Approved"
RESIDUAL RISK ACCEPTANCE
Question | Response
Are all High Risks mitigated? | No
Are all Very High Risks mitigated? | Yes
Is management willing to accept the remaining residual risks? | Yes
Can the project proceed? | Yes
DPO Recommendation | Proceed with Condition
Executive Decision | Proceed with Condition
Approval Conditions | Consult with NDPC on High Risk
SIGN OFF
Approved By
Position
Signature
Approval Date
Next DPIA Review Date

## Executive Dashboard
DATA PROTECTION IMPACT ASSESSMENT (DPIA) DASHBOARD
Project: HealthBridge CareConnect Platform ¦ Organisation: HealthBridge Digital Services Ltd
KPI | Formula
Total Processing Activities | 10
Total Privacy Risks | 10
High & Very High Risks | 1
Overall DPIA Status | Approved
RISK DISTRIBUTION
Residual Risk Rating | Count
Low | 4
Medium | 5
High | 1
Very High | 0
RISKS BY DATA PROTECTION PRINCIPLE
Lawfulness | Column1
Fairness | 0
Transparency | 0
Purpose Limitation | 0
Data Minimisation | 0
Accuracy | 0
Storage Limitation | 0
Integrity & Confidentiality | 8
Accountability | 2
Risk Owner | Count | RISK OWNERS
Data Protection Officer | 0
Information Security Manager | 5
IT Manager | 5
Compliance Officer | 0
Legal Counsel | 0
Operations Manager | 0
APPROVAL DECISIONS
Decision | Count
Approved | 5
Conditionally Approved | 0
Pending Review | 0
Rejected | 0

## Lookup Table
Response | Score | Data Principles | Existing Controls | Likelihood | Score | Impact | Score | Control Effectiveness | Control Effectiveness | Reduction | Risk Owner | Status | Approval | Signature
Yes | 2 | Lawfulness | MFA and Standard Contractual Clauses | Rare | 1 | Insignificant | 1 | Very Effective | Very Effective | 60% | DPO | Open | Approved | Initials
Partially | 1 | Fairness | Encryption and Standard Contractual Clauses | Unlikely | 2 | Minor | 2 | Effective | Effective | 40% | Information Security Manager | In Progress | Conditionally Approved | Name
No | 0 | Transparency | Standard Contractual Clauses | Possible | 3 | Moderate | 3 | Partially Effective | Partially Effective | 20% | IT Manager | Closed | Rejected | "Digitally Approved"
|  | Purpose Limitation | Audit Logs and Standard Contractual Clauses | Likely | 4 | Major | 4 | Ineffective | Ineffective | 0% | Compliance Manager | Accepted | More Information Required
|  | Data Minimisation | Secure Backups and Standard Contractual Clauses | Almost Certain | 5 | Severe | 5 |  |  |  | Project Manager |  | Pending Review
|  | Accuracy | DPA and Standard Contractual Clauses | [7 empty] | Operations Manager
|  | Storage Limitation | Security Awareness and Standard Contractual Clauses
|  | Integrity & Confidentiality | Incident Response Plan and Standard Contractual Clauses
Accountability